PROCESS DESIGN

Cultural Competency Initiative

BROAD COMMUNITY STAKEHOLDERS

Give feedback & input

NAMC

Lead Organization

BLUE RIBBON PANEL

Design, Review, Refine Strategic Plan

PROPOSED PLANNING PROCESS

Multiple Perspectives

Multiple ways to collect information & feedback

Multiple opportunities for discussion & reflection

Outcome-driven

Phase I

March 08-Feb 09

INFORMATION GATHERING

TASKS

Identified diverse stakeholder groups

Held Fall 2008 Conference

Developed one-page summary statement about Initiative

Drafted Process Design

UPDATE TO STAKEHOLDERS

Scheduled and confirmed first Blue Ribbon meeting (2/20/09)

Phase II

Feb – June 2009

CRAFTING THE PLAN FOR THE INITIATIVE

TASKS

Formalize Blue Ribbon Committee

Discuss & prioritize potential programs/strategies and outcomes with key stakeholders

Develop mission, vision and values with key stakeholders and input received from Fall 08 conference participants.

Continue to explore funding prospects for planning phases

Develop financial planning for potential strategies

UPDATES TO STAKEHOLDERS

Phase III

July – Oct 2009

WRITING THE PLAN FOR THE INITIATIVE

TASKS

Revise and refine strategic plan with key stakeholders and get final agreement and approval

The strategic plan articulates:

Vision, Mission and values

Structure of the Initiative

Funding to sustain the Initiative

Priority Focus Area(s)

Priority Strategies

Evaluation Framework ( with measurable outcomes)

UPDATES TO STAKEHOLDERS

Phase IV

Jan– Feb 2010

COMMUNICATING THE PLAN FOR THE INITIATIVE

TASKS

Present plan to key decision-makers including funding agencies

Articulate formal and informal partnerships and collaborations

Phase V

March 2010

IMPLEMENTATION OF PLAN FOR THE INITIATIVE

TASKS

Implement activities as per Strategic Plan

Evaluate progress and outcomes as per Evaluation Framework

# Policy

# Community

Institutional/

Organizational

# Interprsonal/

# Family

Individual and Family